## Sheet1
S.No. | Activity Description | Task Type | Start (Expected) | End (Expected) | Duration(days) elapsed | Status | Remarks
1 | Magento Installation | Dev/Conf | 2014-07-02 | 2014-07-02 | #NAME? | Complete
2 | Documentation of installation steps | Documentation | 2014-07-02 | 2014-07-02 | #NAME? | Complete
3 | Configured vanilla store on local machine using Magento | Dev/Conf | 2014-07-03 | 2014-07-03 | #NAME? | Complete
4 | Understanding backend and front-end functionality of the store | Self-learning | 2014-07-03 | 2014-07-04 | #NAME? | Complete
5 | Identifying target UI design changes (minor) - learning oriented | Analysis | 2014-07-04 | 2014-07-04 | #NAME? | Complete
6 | Making design changes in Magento store | Dev/Conf | 2014-07-07 | 2014-07-07 | #NAME? | Complete
7 | Changing themes with a free downloaded theme | Dev/Conf | 2014-07-08 | 2014-07-09 | #NAME? | Complete
8 | Understanding a theme (layout(.xml files),template(phtml files),locale) (no creation of new themes) | Self-learning | 2014-07-09 | 2014-07-10 | #NAME? | Complete
9 | Category/subcategory creation | Dev/Conf | 2014-07-11 | 2014-07-11 | #NAME? | Complete
10 | Sample product upload - manual product creation | Dev/Conf | 2014-07-14 | 2014-07-14 | #NAME? | Complete
11 | Sample product upload - automated product upload | Dev/Conf | 2014-07-14 | 2014-07-14 | #NAME? | Complete
12 | Product basic image processing | Dev/Conf | 2014-07-14 | 2014-07-14 | #NAME? | Complete
13 | Custom product attributes | Dev/Conf | 2014-07-15 | 2014-07-15 | #NAME? | Complete
14 | Product listing - category wise | Dev/Conf | 2014-07-15 | 2014-07-15 | #NAME? | Complete
15 | Product search filters (various scenarios) | Dev/Conf | 2014-07-15 | 2014-07-15 | #NAME? | Complete
16 | Product sorting (various criteria) | Dev/Conf | 2014-07-16 | 2014-07-16 | #NAME? | Complete
17 | Featured products, most popular products widgets | Dev/Conf | 2014-07-16 | 2014-07-16 | #NAME? | Complete
18 | Product comparison | Dev/Conf | 2014-07-17 | 2014-07-17 | #NAME? | Complete
19 | Product reviews + ratings - Creation and Display | Dev/Conf | 2014-07-18 | 2014-07-18 | #NAME? | Complete
20 | Review moderation | Dev/Conf | 2014-07-18 | 2014-07-18 | #NAME? | Open
21 | Newsletter subscriptioin | Dev/Conf | 2014-07-21 | 2014-07-21 | #NAME? | Complete
22 | Contact Us form | Dev/Conf | 2014-07-21 | 2014-07-21 | #NAME? | Complete
23 | Add/Delete/Update Cart | Dev/Conf | 2014-07-22 | 2014-07-22 | #NAME? | Complete
24 | Cart checkout | Dev/Conf | 2014-07-22 | 2014-07-22 | #NAME? | Complete
25 | Add to Wishlist | Dev/Conf | 2014-07-23 | 2014-07-23 | #NAME? | Complete
Payment Gateway integration
26 | PG integration - PayPal | Dev/Conf | 2014-07-24 | 2014-07-24 | #NAME? | Complete
27 | PG Integration - Identifying the right payment gateway (other than Paypal) | Analysis | 2014-07-25 | 2014-07-25 | #NAME? | Complete
28 | Write a comparison of popular payment gateway systems | Documentation | 2014-07-28 | 2014-07-30 | #NAME? | Open
29 | PG integration - with the identified payment gateway (such as CCAvenue, PayU etc.) | Dev/Conf | 2014-07-30 | 2014-08-01 | #NAME? | Complete
Social Media Integration
30 | Social media authentication - Facebook/Google | Dev/Conf | 2014-08-01 | 2014-08-01 | #NAME? | Complete
31 | Like, Share and Follow - Twitter, Facebook & Google+, Pinterest | Dev/Conf | 2014-08-04 | 2014-08-04 | #NAME? | Complete
Reports
32 | Sales, Shopping cart, products, customers, tags, reviews, search terms, | Dev/Conf | 2014-08-05 | 2014-08-05 | #NAME? | Complete
Web Content Management
33 | Adding new menu items and static pages | Dev/Conf | 2014-08-06 | 2014-08-06 | 1 | Complete
34 | Changing the UI of individual pages | Dev/Conf | 2014-08-07 | 2014-08-07 | 1 | Complete
35 | Creating theme templates for specific pages | Dev/Conf | 2014-08-08 | 2014-08-08 | 1 | Complete
36 | Widgets | Dev/Conf | 2014-08-11 | 2014-08-11 | 1 | Complete
37 | Polls | Dev/Conf | 2014-08-12 | 2014-08-12 | 1 | Complete
Customer Management
38 | Individual Customer Management | Dev/Conf | 2014-08-13 | 2014-08-13 | #NAME? | Complete
39 | Customer Group Creation | Dev/Conf | 2014-08-14 | 2014-08-14 | #NAME? | Complete
40 | Online Customers view | Dev/Conf | 2014-08-14 | 2014-08-14 | #NAME? | Complete
Sales Management
Order Mangement
41 | Order view - Invoice creation, credit memo creation, shipment | Dev/Conf | 2014-08-18 | 2014-08-18 | #NAME? | Complete
42 | Invoice Managmeent - Print and Send Email | Dev/Conf | 2014-08-18 | 2014-08-18 | #NAME? | Complete
43 | Shipment - Print and Send Tracking Information | Dev/Conf | 2014-08-19 | 2014-08-19 | #NAME? | Complete
44 | Transaction management - View/Search/Print | Dev/Conf | 2014-08-20 | 2014-08-21 | #NAME? | Complete
45 | T&C Management - Per store | Dev/Conf | 2014-08-21 | 2014-08-22 | #NAME? | Complete
46 | Taxaction Management - basic | Dev/Conf | 2014-08-22 | 2014-08-22 | #NAME? | Complete
| Mobile Module of Magento |  |  |  | #NAME?
47 | Identification of the entire functionality and the features to be done | Analysis | 2014-08-25 | 2014-08-27 | #NAME? | Open
48 | Documentation - may entail POC creation | Documentation | 2014-08-28 | 2014-08-29 | #NAME? | Open
System Module
Backups
49 | System Backup | Dev/Conf | 2014-09-01 | 2014-09-01 | #NAME?
50 | Database Backup | Dev/Conf | 2014-09-02 | 2014-09-02 | #NAME?
51 | Media Backup | Dev/Conf | 2014-09-02 | 2014-09-02 | #NAME?
Web Services
52 | REST | Dev/Conf | 2014-09-03 | 2014-09-04 | #NAME?
53 | SOAP | Dev/Conf | 2014-09-04 | 2014-09-05 | #NAME?
54 | oAuth | Dev/Conf | 2014-09-05 | 2014-09-05 | #NAME?
Export and Import
55 | Products | Dev/Conf | 2014-09-08 | 2014-09-08 | #NAME?
56 | Customers | Dev/Conf | 2014-09-09 | 2014-09-09 | #NAME?
Permissions
57 | Users | Dev/Conf | 2014-09-10 | 2014-09-10 | #NAME?
58 | roles | Dev/Conf | 2014-09-10 | 2014-09-10 | #NAME?
59 | Cache Management | Dev/Conf | 2014-09-11 | 2014-09-11 | #NAME?
#NAME?
60 | Internationalization and Localization | Dev/Conf | 2014-09-12 | 2014-09-12 | #NAME?
#NAME?
61 | Magento store migration from an older version to the latest version | Analysis + Dev/Conf | 2014-09-15 | 2014-09-16 | #NAME?