## Sheet1
Sr No | Tasks | Status | 2014-10-20 | 2014-10-21 | 2014-10-22 | 2014-10-23 | 2014-10-24 | 2014-10-27 | 2014-10-28 | 2014-10-29 | 2014-10-30 | 2014-10-31 | 2014-11-03 | 2014-11-04 | 2014-11-05 | 2014-11-06 | 2014-11-07
1 | Create a Homepage as a replica from existing application or HTML in Magento. | Complete
2 | Create an Event Module in Magento. Add Event Title, Description, Images, Location, Date, Linking etc. User can register for event. | Complete
3 | User Survey Module in Magento. Admin can add questions for feedback in the survey. Customer can complete survey during Checkout. | Complete | 2014-10-20: AK/HT; 2014-10-21: AK/HT; 2014-10-22: AK/HT; 2014-10-27: AK/AP; 2014-10-28: AK/AP; 2014-10-29: AK/AP; 2014-10-30: AK/AP; 2014-10-31: Complete
4 | Advance search feature similar to gmail search in Magento. | Already existing tried some Customization
5 | ShopGate Mobile Extension. Analyse the extension and try to create an applicaiton for android. | Stuck due to license
6 | Social Media Authentication Extension development | Stuck due to unavailability of staging server
7 | Employee Registration Form in PHP | Complete
8 | Customization on Category and Product Page on Frontend | Complete
9 | Merge User Custom Attribute module with Profile Image module | Complete | 2014-10-20: SP/HT; 2014-10-21: SP/HT; 2014-10-22: SP/HT; 2014-10-27: SP/HT; 2014-10-28: SP/HT; 2014-10-29: SP/HT; 2014-10-30: Complete
10 | Custom Product Attributes Module | Need to Finalize Requirements | 2014-11-03: AK/SP HT/AP; 2014-11-04: AK/SP HT/AP; 2014-11-05: AK/SP HT/AP; 2014-11-06: AK/SP HT/AP; 2014-11-07: AK/SP HT/AP
11 | Document for Salient Features of modules developed | In-Progress | 2014-10-30: SP; 2014-10-31: Complete
12 | How to publish extension on market place | In-Progress | 2014-10-30: AP; 2014-10-31: Complete
13 | Responsive Look & Feel
HIMANSHU | bar: 2014-10-20
ANKUSH | bar: 2014-10-20
ATUL | bar: 2014-10-20
SAURABH | bar: 2014-10-20
RAHUL | bar: 2014-10-20
AMIT | bar: 2014-10-20